## Andriod
Tracking ID | Module/Sub Module/Feature | Environment | Build Version/URL/APK | Credential | Testing Date | Issue Findings (Issue name, Steps to reproduce, Actual Result, Expected Result, Test Data) | Issue Category | Issue Type | Priority | QA Status | QA Name | QA Remarks | Attachments | Reporting Manager's Feedback | Current Iteration | Issue Occurance Count | Developer Name | Issue Status-Developers Feedback | Developer's Remark | Defect Solved Date
1 | App | Physical Device | APP_Link | Username: Sadiqul Gmail: sadiqul159769@gmail.com Password: Pappu1234@ | 28/01/2023 | Actual result: The app is crashing when I am using android 13 Steps To reproduce: 1. Install the app from play store. 2. Open the app. Expected Result: The app should run properly on all android versions. | Bugs | Blocker | High | Open | Pappu | App didn't open properly in all andriod version. | Supporting Attachment
2 | Login with Google | Physical Device | APP_Link | Username: Sadiqul Gmail: sadiqul159769@gmail.com Password: Pappu1234@ | 28/01/2023 | Actual result: When I want to log in with the google account it says it doesn't have google verified Steps To reproduce: 1. Open the app 2. Click Login using Google Expected Result: After pressing the login using Google. It should open the account. | Bugs | Functionality Errors | High | Open | Pappu |  | Supporting Attachment
3 | Login | Physical Device | APP_Link | Username: Sadiqul Gmail: sadiqul159769@gmail.com Password: Pappu1234@ | 29/01/2023 | Actual result: In the login page there is "Create Account" Steps To reproduce: 1. Open the app 2. Click Login Expected Result: In login Page there sould be "Create an Account" | Fine Tuning | GUI Error | High | Open | Pappu |  | Supporting Attachment
4 | Create an Account | BlueStacks | APP_Link | Username: Sadiqul Gmail: sadiqul159769@gmail.com Password: Pappu1234@ Confirm password: Pappu@1234 | 30/01/2023 | Actual result: Create account Functionality properly not working Steps To reproduce: 1. Open the app 2. Click Login 3. Click create an account. Expected Result: Create account Functionality should work properly." | Bugs | Functionality Errors | High | Open | Pappu | Create account functionality doesn't work properly in Bluestack | Supporting Attachment
5 | Create Account | BlueStacks | APP_Link | Username: Sadiqul Gmail: sadiqul159769@gmail.com Password: Pappu1234@ | 30/01/2023 | Actual result: Create account page back button overlap with "create using facebook account" and back button not visible Steps To reproduce: 1. Open the app 2. Click Login 3. Click create an account. Expected Result: The back button should be visible properly. | Fine Tuning | GUI Error | High | Open | Pappu | Back button overlap in physical device | Supporting Attachment
6 | Profile | BlueStacks | APP_Link | Username: Sadiqul Gmail: sadiqul159769@gmail.com Password: Pappu1234@ | 30/01/2023 | "Actual result: After editing, username should be updated Steps To reproduce: 1. Open the app 2. Click Login with valid credential 3. go to profile tab 4. edit profile 5. edit User name 6. Then press save button Expected Result: The USER name should be updated after press the save button | Bugs | Functionality Errors | High | Open | Pappu | Usename can't updated | Supporting Attachment
| Create Event | BlueStacks | APP_Link | Username: Sadiqul Gmail: sadiqul159769@gmail.com Password: Pappu1234@ | 30/01/2023 | "Actual result: After Pressing the start event it works properly Steps To reproduce: 1. Open the app 2. Click Login with valid credential 3. It should redirect to the landing page 4. press create an event 5. start event Expected Result: start event button should work properly | Bugs | Functionality Errors | High | Open | Pappu | Start Event functionality not work | Supporting Attachment
Physical Device

## IOS
Tracking ID | Module/Sub Module/Feature | Environment | Build Version/URL/APP_link | Testing Date | Issue Findings (Issue name, Steps to reproduce, Actual Result, Expected Result, Test Data) | Issue Category | Issue Type | Priority | QA Status | QA Name | QA Remarks | Attachments | Reporting Manager's Feedback | Current Iteration | Issue Occurance Count | Developer Name | Issue Status-Developers Feedback | Developer's Remark | Defect Solved Date
1 | App | Iphone 12 | APP_Link | 28/01/2023 | Actual Result: Cant crate account with Facebook Steps To reproduce: 1. Open the app 2. Login with facebook Expected Result: Should create account with Facebook. | Bugs | Blocker | High | Open | Pappu | App didn't open properly in all andriod version. | Supporting Attachment
2 | Login with Google | Iphone 13 | APP_Link | 28/01/2023 | Actual Result: App crashes when click on "switch to Host" Steps To reproduce: 1. Open the app 2. Login with valid credentian 3. Go to profile 4. Click on Switch to host Expected Result: App should not be crashes when click on "switch to Host" | Bugs | Functionality Errors | High | Open | Pappu |  | Supporting Attachment
3 | Login | Iphone 14 | APP_Link | 29/01/2023 | Actual Result: Username cant be edit in edit profile. Steps To reproduce: 1. Open the app 2. Login with valid credentian 3. Go to profile 4. Click on Switch to host Expected Result: Username can be edit in edit profile. | Fine Tuning | GUI Error | Medium | Open | Pappu |  | Supporting Attachment
4 | Create an Account | Iphone 15 | APP_Link | 30/01/2023 | Actual Result: Feed is always empty Steps To reproduce: 1. Open the app 2. Login with valid credentian 3. Go to feed Expected Result: Feed should not be empty | Bugs | Functionality Errors | High | Open | Pappu | Create account functionality doesn't work properly in Bluestack | Supporting Attachment
5 | Create Account | Iphone 16 | APP_Link | 30/01/2023 | Actual Result: Login page back button does not work Steps To reproduce: 1. Open the app 2. Go to login page Expected Result: Login page back button should work | Fine Tuning | GUI Error | Medium | Open | Pappu | Back button overlap in physical device | Supporting Attachment
6 | Profile |  | APP_Link | 30/01/2023 | Actual Result: In the create Schedule Event page option, Invite user through Email option does not work Steps To reproduce: 1. Open the app 2. Login with valid credential 3. Go to Create event 4. Go to schedule event Expected Result: In the create Schedule Event page Invite Email option should sent email to inputed mail id | Bugs | Functionality Errors | High | Open | Pappu | Usename can't updated | Supporting Attachment